## pmr
ANNEX B
Department of Budget and Management Annual Procurement Plan for FY 2023
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Provide Sound System and Led Wall on Various Socio Cultural Activities held at Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | December 9-21, 2022 |  | December 21, 2023 | December 21, 2023 | December 22, 2023 | December 23-26, 2023 | December 28, 2023 | December 30- January 2, 2023 | January 3, 2023 | January 23, 2023 | January 16, 17, 18, 19, 21, 22 & 23, 2023 | General Fund | 520000 |  | 520000 | 520000 |  | 520000 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | December 21, 2023 | December 21, 2023 | December 22, 2023 | December 23-26, 2023 | January 23, 2023 | Completed
| Tarpaulin Printing for use in various Socio-Cultural Activities, Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-16 | 2023-01-16 |  | 40700 |  |  | 34620
| Purchase of various supplies and materials for use in the Repair of Wire Fence (Interlink), LGU, Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-13 | 2023-01-13 |  | 19250 |  |  | 19250
| Purchase of various Electrical Supplies for use in the Preparation of various activities, LGU, Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-13 | 2023-01-13 |  | 24990 |  |  | 24810
| T-Shirt and T-shirt Printing for use during the Batabalani Festival and Kasalan ng Bayan in Connection with the Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-19 | 2023-01-19 |  | 49850 |  |  | 49100
| Meals for use during the Socio-Cultural Activities (Opening Salvo) on January 16, 2023 at Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-16 | 2023-01-16 |  | 36450 |  |  | 36480
| Purchase of Plaques for use during the Sports and Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-12 |  |  | 2023-01-18 | 2023-01-18 |  | 85500 |  |  | 77500
| Road Concreting, Barangay Bago, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | December 14- January 4, 2023 |  | January 4, 2023 | January 4, 2023 | January 5, 2023 | January 6-10, 2023 | January 12, 2023 | January 16, 2023 | January 18, 2023 |  |  | 20% Development fund | 500000 |  | 500000 | 499499.1 |  | 499499.1 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | January 4, 2023 | January 4, 2023 | January 5, 2023 | January 6-10, 2023
| Procurement for the Repair of Heavy Equipment of LGU, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | December 14- January 4, 2023 |  | January 4, 2023 | January 4, 2023 | January 5, 2023 | January 6-10, 2023 | January 12, 2023 | January 16, 2023 | January 18, 2023 | February 2, 2023 | February 2, 2023 | General Fund | 403500 |  | 403500 | 402450 |  | 402450 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | January 4, 2023 | January 5, 2023 | January 6-10, 2023 | January 12, 2023 | February 2, 2023 | Completed
| Purchase of Mixed Sand and Gravel for use in the Resurfacing of Barangay Road to Dumpsite, Brgy. Ponong, Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-18 | 2023-01-18 |  | 100000 |  |  | 100000
| Purchase of various Electrical Supplies for use in the Street Lighting of Callijon St., Brgy Kalanggaman, Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-16 | 2023-01-16 |  | 81500 |  |  | 81200
| Purchase of various Materials for use in the Rehabilitation of Existing Cottage at the Aroma Beach, Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-16 | 2023-01-16 |  | 60315 |  |  | 60255
| To Provide Meals for the upcoming activities of the Bato Town Fiesta Celebration | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | December 22- January 11, 2023 |  | January 11, 2023 | January 11, 2023 | January 11, 2023 | January 12-13, 2023 | January 16, 2023 | January 17-18, 2023 | January 19, 2023 | January 22, 2023 | January 19, 21 & 22, 2023 | General Fund | 270000 | 270000 |  | 270000 | 270000 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | January 11, 2023 | January 11, 2023 | January 11, 2023 | January 12-13, 2023 | January 22, 2023 | Completed
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at the Holy Child Parish Covered Court, Bato, Leyte on January 22, 2023 | [9 empty] | 2023-01-16 |  |  | 2023-01-19 | 2023-01-19 |  | 12750 |  |  | 11805
| Meal and snacks for use during the 2023 Voluntary Blood Donation Activity held at the Holy Child Parish Covered Court, Bato, Leyte on January 22, 2023 | [9 empty] | 2023-01-16 |  |  | 2023-01-22 | 2023-01-22 |  | 17500 |  |  | 17500
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at the Holy Child Parish Covered Court, Bato, Leyte on January 22, 2023 | [9 empty] | 2023-01-16 |  |  | 2023-01-18 | 2023-01-18 |  | 1000 |  |  | 1000
| Purchase of supply and material for use in the Office of the Municipal Accountant, Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-20 | 2023-01-20 |  | 5900 |  |  | 5900
| Purchase of Medicines for use in the National Tuberculosis Program, Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-23 | 2023-01-23 |  | 29480 |  |  | 29424
| Tarpaulin Printing for use in the Information, Education and Communication Material for the Solid Waste Management Program of Bato, Leyte | [9 empty] | 2023-01-10 |  |  | 2023-01-18 | 2023-01-18 |  | 792 |  |  | 792
| Meals for use during the Batobalani/Tourism Jingle Video Shoots on January 23-25, 2023 at Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-23 | 2023-01-23 |  | 30000 |  |  | 30000
| Meal and Snacks for use during the Orientation on Livelihood Skills Training for Indigenous "Badjao", Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-20 | 2023-01-20 |  | 39000 |  |  | 39000
| Purchase of Basketball Uniform for use during the Sports and Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-19 | 2023-01-19 |  | 49500 |  |  | 49500
| Professional and Service Fee for Visual Graphics and Animation during the LGU Night in connection with the Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-13 |  |  | 2023-01-19 | 2023-01-19 |  | 12500 |  |  | 12500
| Meal and Snacks for use during the Distribution of UCT Cash Card, Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-26 | 2023-01-26 |  | 7000 |  |  | 7000
| Meal and Snacks for use during the Conduct of Geological Assessment/Site Scoping of the Proposed Sanitary Landfill Site in Brgy. Amagos, Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-20 | 2023-01-20 |  | 2800 |  |  | 2800
| Tent Rental for use on Various Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-16 |  |  | 2023-01-24 | 2023-01-24 |  | 49950 |  |  | 49950
| Purchase of Laboratory Supplies for use in the Bato Diagnostic Center, Bato, Leyte | [9 empty] | 2023-01-23 |  |  | 2023-01-31 | 2023-01-31 |  | 8850 |  |  | 8844
| Purchase of spare parts for use in the Repair of LGU Concrete Mixer and Concrete Vibrator for the Concreting of Pathway, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-01-26 |  |  | 2023-02-03 | 2023-02-03 |  | 66700 |  |  | 66700
| Purchase of Mixed Sand and Gravel for use in Resurfacing of Sitio Upper Canlambong, Brgy. Ponong, Bato, Leyte | [9 empty] | 2023-01-26 |  |  | 2023-01-31 | 2023-01-31 |  | 100000 |  |  | 100000
| Purchase of Mixed Sand and Gravel for use in Resurfacing of Sitio Puthaw to Sitio Can-idlang Road, Brgy. Tabunok, Bato, Leyte | [9 empty] | 2023-01-26 |  |  | 2023-01-30 | 2023-01-30 |  | 100000 |  |  | 100000
| Purchase of LGU- Uniform (Polo Type & Long Sleeve) for LGU Employee of Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | January 23- February 13, 2023 |  | February 13, 2023 | February 13, 2023 | February 14, 2023 | February 15-17, 2023 | February 21, 2023 | February 23-24, 2023 | February 27, 2023 | February 28, 2023 | February 28, 2023 | General Fund | 140000 | 140000 |  | 138320 | 138320 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | February 13, 2023 | February 13, 2023 | February 14, 2023 | February 15-17, 2023 | February 28, 2023 | Completed
| Procurement of 4-Unit Brand New (6x4, 10 wheeler) Dumptruck for use in the Municipality of Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | July 12- August 2, 2023 | July 20, 2023 | August 2, 2023 | August 2, 2023 | August 3, 2023 | August 4-10, 2023 | August 14, 2023 | August 16-17, 2023 | August 18, 2023 | September 20, 2023 | September 20, 2024 | General Fund/ DBP Loan | 25200000 |  | 25200000 | 24780000 |  | 24780000 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | August 2, 2023 | August 2, 2023 | August 3, 2023 | August 4-10, 2023 | September 20, 2024 | Completed
| Purchase of Mixed Sand and Gravel for use in Resurfacing of Brgy. Tagaytay to Brgy. San Agustin Road, Bato, Leyte | [9 empty] | 2023-01-26 |  |  | 2023-01-30 | 2023-01-30 |  | 100000 |  |  | 100000
| Purchase of Mixed Sand and Gravel for use in Resurfacing of Brgy. Sto. Niño Road, Bato, Leyte | [9 empty] | 2023-01-26 |  |  | 2023-01-30 | 2023-01-30 |  | 100000 |  |  | 100000
| Professional and Service Fee for Choreography and Drummer Service during the Dance Offering in connection with the Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-01-19 | [8 empty] | 59000
| Professional and Service Fee for Hair, Make-up and Costume Rental Service Package during the Dance Presentation in connection with the Socio-Cultural Activities at Bato, Leyte | [9 empty] | 2023-01-19 | [8 empty] | 59000
| Snacks for use during the Orientation for the 4P's Set 12-A Registration, Bato, Leyte | [9 empty] | 2023-01-27 |  |  | 2023-01-30 | 2023-01-30 |  | 5000 |  |  | 5000
| Snacks for use during the Information Education Communication (IEC) of Solid Waste Management conducted by DENR-EMB, RO8 Personnel, Bato, Leyte | [9 empty] | 2023-01-27 |  |  | 2023-01-21 | 2023-01-21 |  | 8000 |  |  | 8000
| Newborn Screening Kit and Lancets for use in the Newborn Screening - Maternity Care Package, Rural Health Unit, Bato, Leyte | [9 empty] | 2023-02-06 | [8 empty] | 17700
| Purchase of Construction Supplies for use in the Installation of New Barrier and Fence, Bato Port, Bato, Leyte | [9 empty] | 2023-02-06 |  |  | *2/29 | *2/29 |  | 20450 |  |  | 20330
| Purchase of Hematology Reagent and Control for use in the Bato Diagnostic Center, Bato, Leyte | [9 empty] | 2023-02-09 |  |  | 2023-02-16 | 2023-02-16 |  | 99000 |  |  | 99000
| Maintenance of Airconditioning Unit for use in the COMELEC Office, LGU, Bato, Leyte | [9 empty] | 2023-02-06 |  |  | 2023-02-08 | 2023-02-08 |  | 900 |  |  | 850
| Maintenance of Airconditioning Unit for use in the Office of the Municipal Accountant, LGU, Bato, Leyte | [9 empty] | 2023-02-06 |  |  | 2023-02-08 | 2023-02-08 |  | 700 |  |  | 700
| Maintenance of Air-conditioning Unit for use in the Port Office, LGU, Bato, Leyte | [9 empty] | 2023-02-06 |  |  | 2023-02-08 | 2023-02-08 |  | 3100 |  |  | 3000
| Meal for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Osmeña, Bato, Leyte on Feb. 17, 2023 | [9 empty] | 2023-02-13 |  |  | 2023-02-17 | 2023-02-17 |  | 2000 |  |  | 2000
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Osmeña, Bato, Leyte on Feb. 17, 2023 and Bato Institute of Science and Technology (BIST), Brgy. Dolho, Bato, Leyte on Feb. 18, 2023 | [9 empty] | 2023-02-13 |  |  | 2023-02-15 | 2023-02-15 |  | 2000 |  |  | 2000
Diesel
| Supply and Delivery of Various Materials for the Renovation of Bato Port Terminal Bldg., Brgy. Iniguihan, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | February 15- March 7, 2023 |  | March 7, 2023 | March 7, 2023 | March 8, 2023 | March 9-13, 2023 | March 15, 2023 | March 17, 2023 | March 21, 2023 | March 28, 2023 | March 27 & 28, 2023 | General Fund | 212051 | 212051 |  | 211865 | 211865 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | March 7, 2023 | March 7, 2023 | March 8, 2023 | March 9-13, 2023 | March 28, 2023 | Completed
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Osmeña, Bato, Leyte on Feb. 17, 2023 and Bato Institute of Science and Technology (BIST), Brgy. Dolho, Bato, Leyte on Feb. 18, 2023 | [9 empty] | 2023-02-13 |  |  | 2023-02-15 | 2023-02-15 |  | 34000 |  |  | 31810
| Purchase of Ink, Master, and Toner for use of the Photocopier and Printer, LGU, Bato, Leyte | [9 empty] | 2023-02-13 |  |  | 2023-02-16 | 2023-02-16 |  | 49000.72 |  |  | 49000.72
| Tarpaulin Printing for use during the Training-Workshop on iClinicSys, Bato, Leyte | [9 empty] | 2023-02-13 |  |  | 2023-02-20 | 2023-02-20 |  | 1350 |  |  | 1296
| Purchase of Training Materials for use during the Training-Workshop on iClinicSys, Bato, Leyte | [9 empty] | 2023-02-13 |  |  | 2023-02-20 | 2023-02-20 |  | 3740 |  |  | 2590
| Room Accommodation for use of the Trainer conducting Training-Workshop on iClinicSys, Bato, Leyte | [9 empty] | 2023-02-17 |  |  | 2023-02-23 | 2023-02-23 |  | 3600 |  |  | 3298.97
| Meals and Snacks for use during the Training-Workshop on iClinicSys, Bato, Leyte | [9 empty] | 2023-02-13 |  |  | 2023-02-24 | 2023-02-24 |  | 26250 |  |  | 26250
| Meals and Snacks for use during the GAD Planning and Budgeting Orientation for CY 2024 on Feb. 21, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-02-16 |  |  | 2023-02-21 | 2023-02-21 |  | 22500 |  |  | 22500
| Meal and snacks for use during the Coastal Clean-up 2023 at Bato Baywalk Area, Bato, Leyte | [9 empty] | 2023-02-20 |  |  | 2023-02-23 | 2023-02-23 |  | 98400 |  |  | 98400
| Meal and Snacks for use during the Enhanced Managing Police Operation Conference in the 5th District of Leyte on February 22, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-02-20 |  |  | 2023-02-22 | 2023-02-22 |  | 40000 |  |  | 40000
| Purchase of Parts for the Repair and Maintenance of the Photocopier use in the Civil Registrar's Office, Bato, Leyte | [9 empty] | 2023-02-27 |  |  | 2023-03-04 | 2023-03-04 |  | 6075 |  |  | 6075
| Purchase of Supplies and Services for the Repair and Maintenance of the Photocopier use in the Office of the Municipal Accountant, LGU, Bato, Leyte | [9 empty] | 2023-02-27 |  |  | 2023-03-04 | 2023-03-04 |  | 12685 |  |  | 12685
| Purchase of Drugs and Medicines for RHU- Bato, Leyte | Rural Health Unit/ Dr. Probo P. Quijano | Public Bidding |  | February 20-March 13, 2023 |  | March 13, 2023 | March 13, 2023 | March 14, 2023 | March 15-17, 2023 | March 21, 2023 | March 23-24, 2023 | March 27, 2023 | July 4, 2023 | April 5 & 24, May 5 & 23, July 4, 2023 | General Fund | 1081583 | 1081583 |  | 1070123 | 1070123 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | March 13, 2023 | March 13, 2023 | March 14, 2023 | March 15-17, 2023 | July 4, 2023 | Completed
| Purchase of Mixed Sand and Gravel for use in Resurfacing of Barangay Road, Junction National Highway Brgy. Anahawan to Brgy. Himama-a, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 03/09 - 03/10 | 03/09 - 03/10 |  | 100000 |  |  | 100000
| Purchase of various Engine Oils and Lubricants for use as Vehicle Maintenance (Change Oil) of LGU Ambulance (Nissan), Bato, Leyte | [9 empty] | 2023-03-06 | [8 empty] | 11450
| Meals and Snacks during the Blessing and Turn-over Ceremony of Sea Ambulance and Infirmary on March 10, 2023, Bato, Leyte | [9 empty] | 2023-03-07 |  |  | 2023-03-10 | 2023-03-10 |  | 55000 |  |  | 55000
| Purchase of various supplies for use during the Blessing and Turn-over Ceremony of Sea Ambulance and Infirmary on March 10, 2023 | [9 empty] | 2023-03-06 |  |  | 2023-03-09 | 2023-03-09 |  | 22400 |  |  | 20704
| Purchase of various supplies for Environmental Sanitation Program in the Municipal Health Office, LGU, Bato, Leyte | [12 empty] | 2023-05-17 | 2023-05-17 |  | 29508 |  |  | 24540
| Purchase of various Dental Supplies for the Dental Program in the Municipal Health Office, LGU, Bato, Leyte | [18 empty] | 34620
| Purchase of various medical supplies for the Family Planning Services in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 2023-05-15 | 2023-05-15 |  | 49800 |  |  | 49210
| Purchase of various medical supplies for Expanded Program on Immunization in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 2023-05-17 | 2023-05-17 |  | 49475 |  |  | 48450
| Purchase of various medical supplies for COVID-19 Program in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 2023-05-15 | 2023-05-15 |  | 49972.5 |  |  | 48500
| Purchase of Medical Supplies for STI/HIV Services in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 2023-05-15 | 2023-05-15 |  | 50000 |  |  | 44350
| Purchase of Construction Supplies for use in the Drainage Canal Cover at the Back of Salazar Rice Mill, Bato, Leyte | [9 empty] | 2023-03-06 |  |  | 2023-03-13 | 2023-03-13 |  | 17500
| Procurement of Fuel, Oil & Lubricants for the consumption of Various LGU- Vehicle of Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | February 7- Febuary 28, 2023 |  | February 28, 2023 | February 28, 2023 | March 1, 2023 | March 2-3, 2023 | March 7, 2023 | March 10, 2023 | March 13, 2023 |  |  | General Fund | 3000000 | 3000000 |  | 2999985 | 2999985 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | February 28, 2023 | February 28, 2023 | March 1, 2023 | March 2-3, 2023 |  | Completed
| Purchase of various medicines for Mental Health Services in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-09 |  |  | 2023-03-27 | 2023-03-27 |  | 74687 |  |  | 63750
| Purchase of various medicines for Animal Bite Management in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-09 |  |  | 2023-04-19 | 2023-04-19 |  | 74000 |  |  | 63210
| Purchase of various medicines for TB Program Services in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-03-09 |  |  | 2023-05-17 | 2023-05-17 |  | 72300 |  |  | 65470
| Supply and Delivery of Various Materials for the Construction of Mabini Spillway, Brgy. Mabini, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | March 11-31, 2023 |  | March 31, 2023 | March 31, 2023 | April 3, 2023 | April 4-5, 2023 | April 12, 2023 | April 17, 2023 | April 18, 2023 | April 27, 2023 | April 18, 19, 20, 24, 27, 2023 | 20% Development Fund | 3576470 |  | 3576470 | 3575880 |  | 3575880 |  |  | March 31, 2023 | March 31, 2023 | April 3, 2023 | April 4-5, 2023 | April 27, 2023 | Completed
| Meal for use during the Municipal Development Council (MDC) Meeting on March 15, 2023, at the 3rd Floor Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-03-10 |  |  | 2023-03-15 | 2023-03-15 |  | 21000 |  |  | 4000
| Snacks for use during the Consultative Conference and Orientation for all Water Refilling Station Owner on March 20, 2023, Bato, Leyte | [9 empty] | 2023-03-13 |  |  | 2023-03-22 | 2023-03-22 |  | 4000 |  |  | 5590
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Ponong, Bato, Leyte on March 24, 2023 | [9 empty] | 2023-03-20 |  |  | 2023-03-20 | 2023-03-20 |  | 6250 |  |  | 2000
| Meal for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Ponong, Bato, Leyte on March 24, 2023 | [9 empty] | 2023-04-17 |  |  | 2023-03-20 | 2023-03-20 |  | 2000 |  |  | 1000
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Ponong, Bato, Leyte on March 24, 2023 | [9 empty] | 2023-03-20 |  |  | 2023-03-23 | 2023-03-23 |  | 1000 |  |  | 1000
| Meal and Snacks for use during the Joint Geological Site Scoping/Assessment for the Proposed Sanitary Landfill in Brgy. Tagaytay, Bato, Leyte conducted by MGB and EMB of DENR on March 24, 2023 | [9 empty] | 2023-03-20 |  |  | 2023-03-24 | 2023-03-24 |  | 3000 |  |  | 3000
| Snacks for use during the Buntis Congress in connection with the Women's Month Celebration held on March 29, 2023 at Bato, Leyte | [9 empty] | 2023-03-24 |  |  | 2023-03-29 | 2023-03-29 |  | 5000 |  |  | 5000
| Tarpaulin Printing, Balloons and Decorations for use during the Buntis Congress in connection with the Women's Month Celebration held on March 29, 2023 at Bato, Leyte | [9 empty] | 2023-03-24 |  |  | 2023-03-28 | 2023-03-28 |  | 1000 |  |  | 1000
| Purchase of various Medical Supplies for use in the Buntis Congress in connection with the Women's Month Celebration held on March 29, 2023 at Bato, Leyte | [9 empty] | 2023-03-24 |  |  | 2023-03-28 | 2023-03-28 |  | 15020 |  |  | 14845
| Meal and snacks for use during the Coastal Clean-up 2023 held on March 31, 2023 at Bato Baywalk Area, Bato, Leyte | [9 empty] | 2023-03-28 |  |  | 2023-03-31 | 2023-03-31 |  | 90000 |  |  | 90000
| Purchase of Construction Supplies for use in Concreting of Pathway at Tabunok Elementary School, Brgy. Tabunok, Bato, Leyte | [9 empty] | 2023-03-28 |  |  | 2023-04-03 | 2023-04-03 |  | 11200 |  |  | 11200
| Purchase of various materials for use in the Rehabilitation of Municipal Street Lighting, Bato, Leyte | [9 empty] | 2023-03-30 |  |  | 2023-04-03 | 2023-04-03 |  | 50780 |  |  | 50650
| Meals and Snacks for use during the Tulong Panghanapbuhay sa Ating Disadvantaged/Displaced(TUPAD) Workers' Payout held on April 4, 5, and 11, 2023 at Bato, Leyte | [9 empty] | 2023-04-03 |  |  | April 4,5 & 11 | April 4,5 & 11 |  | 18000 |  |  | 54000
| Supply and Delivery of Various Materials for the Construction of Concrete Drainage Canal, Poblacion, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | March 30- April 20, 2023 |  | April 20, 2023 | April 20, 2023 | April 21, 2023 | April 24-26, 2023 | April 28, 2023 | May 4, 2023 | May 5, 2023 | May 11, 2023 | May 11, 2023 | 20% Development Fund/ Continuing | 345770 |  | 345770 | 345480 |  | 345480 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | April 20, 2023 | April 20, 2023 | April 21, 2023 | April 24-26, 2023 | May 11, 2023 | Completed
| Purchase of Medical Oxygen for use in the Municipal Health Unit, Bato, Leyte | [9 empty] | 2023-04-12 |  |  | 2023-04-19 | 2023-04-19 |  | 10500 |  |  | 10200
| Purchase of various Construction Supplies for use in the Rehabilitation of Comfort Rooms at Sto. Niño Elementary School, Brgy. Sto. Niño, Bato, Leyte | [9 empty] | 2023-04-12 |  |  | 2023-04-18 | 2023-04-18 |  | 31450 |  |  | 31250
| Purchase of various Construction Supplies for use in the Rehabilitation of Cebuana Primary School, Brgy. Cebuana, Bato, Leyte | [9 empty] | 2023-04-12 |  |  | 2023-04-18 | 2023-04-18 |  | 40750 |  |  | 40650
| Purchase of Mixed Sand and Gravel for use in Backfilling of Balay Silingan Reformation Center, Brgy. Tabunok, Bato, Leyte | [9 empty] | 2023-04-13 |  |  | 2023-04-17 | 2023-04-17 |  | 100000 |  |  | 100000
| Purchase of Construction Supplies for use in the Rehabilitation of Talisayan Primary School, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-04-13 |  |  | 2023-04-18 | 2023-04-18 |  | 54910 |  |  | 54680
| Meal and snacks for use during the Team Building Activity of LGU Officials and Employees, Bato, Leyte | [9 empty] | 2023-04-12 |  |  | 2023-04-14 | 2023-04-14 |  | 99900 |  |  | 99900
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Amagos, Bato, Leyte on April 20, 2023 | [9 empty] | 2023-04-17 |  |  | 2023-04-19 | 2023-04-19 |  | 12600 |  |  | 11680
Meal for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Amagos, Bato, Leyte on April 20, 2023
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Amagos, Bato, Leyte on April 20, 2023 | [9 empty] | 2023-04-17 |  |  | 2023-04-19 | 2023-04-19 |  | 1000 |  |  | 1000
Purchase of Newborn Screening Kit for use in the Newborn Screening - Maternity Care Package, Rural Health Unit, Bato, Leyte
| Purchase of Mixed Sand and Gravel for use in Backfilling of LGU Motorpool (New Site), Brgy. Bagongbayan, Bato, Leyte | [9 empty] | 2023-04-26 |  |  | 2023-05-02 | 2023-05-02 |  | 100000 |  |  | 100000
| Purchase of various supplies for use in the Maintenance of Evacuation Center of LGU, Brgy. Bagongbayan, Bato, Leyte | [9 empty] | 2023-04-27 |  |  | 2023-05-05 | 2023-05-05 |  | 77780 |  |  | 77670
| Purchase of Electrical Supplies for use in the Street Lighting along Jose Rizal St. (National Highway), Bato, Leyte | [9 empty] | 2023-04-27 |  |  | 2023-05-02 | 2023-05-02 |  | 93780 |  |  | 93390
| Construction of 12 Units Commercial Stalls and Improvement of Municipal Gym, Brgy. Iniguihan. Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | April 24- May 10, 2023 |  | May 10, 2023 | May 10, 2023 | May 11, 2023 | May 11-15, 2023 | May 17, 2023 | May 9-22, 2023 | May 23, 2023 | August 8, 2023 | August 8, 2023 | 20% Development Fund | 3999985.92 |  | 3999985.92 | 3997483.77 |  | 3997483.77 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | May 10, 2023 | May 10, 2023 | May 11, 2023 | May 11-15, 2023 | August 8, 2023 | Completed
| Tarpaulin, T-shirt and Sweatshirt Printing for use during the MR-OPV Special Immunization Activity (Chikiting Ligtas 2023) | [9 empty] | 2023-04-24 |  |  | 2023-04-28 | 2023-04-28 |  | 45414 |  |  | 45414
| Purchase of Industrial Acetelyn and Industrial Oxygen for use in the LGU Motorpool, Bato, Leyte | [9 empty] | 2023-05-02 |  |  | 2023-05-10 | 2023-05-10 |  | 8900 |  |  | 6380
| Tarpaulin Printing for use during the TUPAD Payout, Bato, Leyte | [9 empty] | 2023-05-02 |  |  | 2023-05-10 | 2023-05-10 |  | 1422 |  |  | 1422
| Purchase of 12 Volt Battery for use in the Service Vehicle (Ford Everest) of LGU, Bato, Leyte | [9 empty] | 2023-05-02 |  |  | 2023-05-10 | 2023-05-10 |  | 14050 |  |  | 14050
| Purchase of Tire Wheel for use as Vehicle Maintenance of Doris Jeep of LGU, Bato, Leyte | [9 empty] | 2023-05-04 |  |  | 2023-05-11 | 2023-05-11 |  | 55800 |  |  | 55800
| Purchase of Tire Wheel for use as Vehicle Maintenance of Rescue Vehicle of LGU, Bato, Leyte | [9 empty] | 2023-05-04 |  |  | 2023-05-11 | 2023-05-11 |  | 65480 |  |  | 65480
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Dawahon, Bato, Leyte on May 12, 2023 and Brgy Dolho, Bato, Leyte on May 19, 2023 | [9 empty] | 2023-05-08 |  |  | 2023-05-10 | 2023-05-10 |  | 34000 |  |  | 31810
| Meals and Snacks for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Dawahon, Bato, Leyte on May 12, 2023 and Brgy Dolho, Bato, Leyte on May 19, 2023 | [9 empty] | 2023-05-08 |  |  | 2023-05-12 | 2023-05-12 |  | 23000 |  |  | 23000
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Dawahon, Bato, Leyte on May 12, 2023 and Brgy Dolho, Bato, Leyte on May 19, 2023 | [9 empty] | 2023-05-08 |  |  | 2023-05-10 | 2023-05-10 |  | 2000 |  |  | 2000
| Room Accommodation for use of the Provincial Agriculture Office Personnel during the Conduct of Corn and Livestock Integration Training on May 11-12, 2023, Bato, Leyte | [9 empty] | 2023-05-08 |  |  | 2023-05-11 | 2023-05-11 |  | 2300 |  |  | 1855.67
| Purchase of Laboratory Supplies for use in the Bato Diagnostic Center, LGU, Bato, Leyte | [9 empty] | 2023-05-11 |  |  | 2023-05-17 | 2023-05-17 |  | 64000 |  |  | 63700
| Meal and Snacks for use during the TUPAD Payout on May 11, 2023 at Bato, Leyte | [9 empty] | 2023-05-08 |  |  | 2023-05-11 | 2023-05-11 |  | 18000 |  |  | 18000
| Meal for use during the Coastal Clean-up 2023 held on May 19, 2023 at Bato Baywalk Area, Bato, Leyte | [9 empty] | 2023-05-16 |  |  | 2023-05-19 | 2023-05-19 |  | 82500 |  |  | 82500
| Purchase of Diesel for use in the Consumption of Service Vehicle (Nissan Navara) for Hauling Tilapia Fry from Babatngon Hatchery, Babatngon, Leyte for the Dispersal to the Inland Farmers of Bato, Leyte | [9 empty] | 2023-05-12 |  |  | 2023-05-16 | 2023-05-16 |  | 6400 |  |  | 4416
| Meal and Snacks for use during the Banana Stakeholders and Facilitators Meeting from DA PRDP RPCO 8 on May 16, 2023, Bato, Leyte | [9 empty] | 2023-05-12 |  |  | 2023-05-16 | 2023-05-16 |  | 6000 |  |  | 6000
agricultural supplies
| Procurement of Various Office Supplies and Consumables for use in the Officer of LGU- Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | February 22- March 15, 2023 |  | March 15, 2023 | March 15, 2023 | March 16, 2023 | March 17-21, 2023 | March 23, 2023 | March 28, 2023 | March 29, 2023 | April 4, 2023 | April 4, 2023 | General fund | 1237011.24 | 1237011.24 |  | 1236844.24 | 1236844.24 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | March 15, 2023 | March 15, 2023 | March 16, 2023 | March 17-21, 2023 | April 4, 2023 | Completed
| Snacks for use during the Mid-Activity Assessment for MR-OPV SIA (Chikiting Ligtas 2023), Bato, Leyte | [9 empty] | 2023-05-12 |  |  | 2023-05-18 | 2023-05-18 |  | 19500 |  |  | 19500
| Synthetic Oils for use in Changing Oil of 2-unit LGU Ambulance, Bato, Leyte | [9 empty] | 2023-05-15 | [8 empty] | 15350
| Meals and Snacks for use during the Social Pension Payout for the Senior Citizens' on May 22 - 26, 2023 at Bato, Leyte | [9 empty] | 2023-05-18 |  |  | May 22,23, 24,25 26 | May 22,23, 24,25 26 |  | 100000 |  |  | 100000
| Purchase of Diesel for use in the Consumption of LGU Dumptruck in Hauling of Rice and Corn Seeds from DA-RIARC, Abuyog Leyte for Distribution to Bato Rice Farmers under DA Masagana Rice Program of Bato, Leyte | [9 empty] | 2023-05-29 |  |  | 2023-05-31 | 2023-05-31 |  | 6400 |  |  | 4528
Meals and Snacks for use during the Data Build-Up in Preparation for 2019 PSIC Migration on June 05-06, 2023, Bato, Leyte
| Room Accommodation for use of the DICT Personnel during the Conduct of Data Build-Up Assistance in Preparation for 2019 PSIC Migration, Bato, Leyte | [9 empty] | 2023-05-29 |  |  | 2023-06-05 | 2023-06-05 |  | 2000 |  |  | 2000
| Purchase of various Materials for use in the Improvement of 2-Unit Evacuation Center (Dirty Kitchen, Comfort Room and Septic Tank) at Brgy. Bagongbayan, Bato, Leyte | [9 empty] | 2023-06-08 |  |  | 2023-06-15 | 2023-06-15 |  | 63600 |  |  | 63325
| Purchase of Diesel for use in the Consumption of Doris Jeepney while Transporting the Members of Bato Senior Citizens Federation during their Team Building held in Baybayon Nato, Guadalupe, Inopacan, Leyte on June 5, 2023 | [15 empty] | CANCELLED
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Anahawan, Bato, Leyte on June 16, 2023 and Brgy. Iniguihan, Bato, Leyte on June 22, 2023 | [9 empty] | 2023-06-09 |  |  | 2023-06-15 | 2023-06-15 |  | 14400 |  |  | 13020
Meal and Snacks for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Anahawan, Bato, Leyte on June 16, 2023
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Anahawan, Bato, Leyte on June 16, 2023 and Brgy. Iniguihan, Bato, Leyte on June 22, 2023 | [9 empty] | 2023-06-09 |  |  | 2023-06-15 | 2023-06-15 |  | 2000 |  |  | 2000
| Purchase of various Construction Materials for use in the School Beautification at Alejos Elementary School, Brgy. Alejos, Bato, Leyte | [9 empty] | 2023-06-09 |  |  | 2023-06-15 | 2023-06-15 |  | 32010 |  |  | 31935
| Procurement of Various Office Supplies and Consumables for the 2nd Quarter of 2023, LGU- Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | May 11- June 1, 2023 |  | June 1, 2023 | June 1, 2023 | June 2, 2023 | June 5-7, 20230 | June 9, 2023 | June 14-15, 2023 | June 16, 2023 | July 3, 2023 | June 29, July 3, 2023 | General Fund | 118773 | 118773 |  | 118743 | 118743 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | June 1, 2023 | June 1, 2023 | June 2, 2023 | June 5-7, 20230 | July 3, 2023 | Completed
Purchase of various Electrical Materials for use in the Maintenance of Electrical Lightings at the Public Market, Public Terminal and Evacuation Center, Bato, Leyte
| Purchase of Painting Supplies for use in Repainting of the Sea Ambulance, Bato, Leyte | [9 empty] | 2023-06-13 |  |  | 2023-06-15 | 2023-06-15 |  | 2520 |  |  | 2460
| Purchase of various Automotive Supplies for use in Changing Oil of Rescue Vehicle (Nissan Navara, Plate # HAB 8647), Bato, Leyte | [9 empty] | 2023-06-13 |  |  | 2023-06-19 | 2023-06-19 |  | 5980 |  |  | 5980
| Purchase of various Materials for use in the Rehabilitation of Public Comfort Rooms (Port, Wet Market, Bus Terminal), Bato, Leyte | [9 empty] | 2023-06-14 |  |  | 2023-06-21 | 2023-06-21 |  | 99630 |  |  | 99450
Purchase of Various Painting Supplies for use in Painting of Border Line at Bato Public Market, Bato, Leyte
Meal and Snacks for use during the Mobile X-Ray in connection with the TB Program held at the Evacuation, Center, Bato, Leyte
| Tarpaulin Printing for use during the Dengue Awareness Month (Environmental Sanitation), Bato, Leyte | [9 empty] | 2023-06-14 |  |  | 2023-06-16 | 2023-06-16 |  | 1446 |  |  | 1296
| Tarpaulin Printing for use in Posting the 2023 Updated LGU Bato Citizen's Charter, Bato, Leyte | [9 empty] | 2023-06-19 |  |  | 2023-06-27 | 2023-06-27 |  | 3600 |  |  | 3456
Meals and Snacks for use during the Emergency Shelter Assistance (ESA) Ayuda Payout on June 26-29, 2023 at Bato, Leyte
Meal for use during the Leyte Association of Municipal Nutrition Action Officers (LAMNAO) Meeting - Benchmarking held at Bato, Leyte
Meal and Snacks for use during the Annual Capacity Enhancement and Team Building Activity, RHU, Bato, Leyte
| Purchase of Tire Wheel for use as Vehicle Maintenance of the Service Utility Vehicle (Ford Everest) of LGU, Bato, Leyte | [9 empty] | 2023-06-22 |  |  | 2023-06-29 | 2023-06-29 |  | 75500 |  |  | 75500
| Tarpaulin Printing for use in 4P's Graduation Ceremony - Pugay Tagumpay, Bato, Leyte | [9 empty] | 2023-06-23 |  |  | 2023-06-27 | 2023-06-27 |  | 600 |  |  | 576
| Purchase of Heavy Duty Door Knob for use in the Auditor's Office, LGU, Bato, Leyte | [9 empty] | 2023-06-26 |  |  | 2023-07-04 | 2023-07-04 |  | 2000 |  |  | 2000
| Tarpaulin and T-shirt Printing for use during the 2023 Nutrition Month Celebration Launching Activity, Bato, Leyte | [9 empty] | 2023-06-26 |  |  | 2023-06-30 | 2023-06-30 |  | 39420 |  |  | 39420
| Purchase of Laptop for use in iTax in the Office of the Municipal Assessor, LGU, Bato, Leyte | [9 empty] | 2023-07-04 |  |  | 2023-07-06 | 2023-07-06 |  | 80000 |  |  | 80000
| Purchase of Laptop for use in iTax in the Office of the Municipal Treasurer, LGU, Bato, Leyte | [9 empty] | 2023-07-04 |  |  | 2023-07-07 | 2023-07-07 |  | 80000 |  |  | 80000
| Supplies and Tarpaulin Printing for use as Giveaway for the Regional Assessment Team during the 2023 SGLG Assessment for the Municipality of Bato, Leyte on July 05, 2023. | [9 empty] | 2023-06-30 |  |  | 2023-07-04 | 2023-07-04 |  | 100000 |  |  | 4282
| Meal and Snacks for use of the Regional Assessment Team and LGU Officials during the 2023 SGLG Assessment for the Municipality of Bato, Leyte on July 05, 2023 | [9 empty] | 2023-07-03 |  |  | 2023-07-05 | 2023-07-05 |  | 15750 |  |  | 15750
| Purchase of IT Supplies for use in the ECCD Office, Bato, Leyte | [9 empty] | 2023-07-03 |  |  | 2023-07-06 | 2023-07-06 |  | 16000 |  |  | 16000
| Purchase of various Construction Materials for use in the Water System, Comfort Rooms Wet Market Building, Brgy. Iniguihan, Bato, Leyte | [9 empty] | 2023-07-03 |  |  | 2023-07-06 | 2023-07-06 |  | 7974 |  |  | 7900
| Purchase of various materials for use in the Repair of Damaged Pavement at Brgy. Sto Niño, Bato, Leyte | [9 empty] | 2023-07-06 |  |  | 2023-07-10 | 2023-07-10 |  | 96300 |  |  | 96300
| Purchase of various materials for use in the Rehabilitation of Drainage Canal along Municipal Streets, Poblacion, Bato, Leyte | [9 empty] | 2023-07-06 |  |  | 2023-07-10 | 2023-07-10 |  | 93020 |  |  | 93020
| Room Accommodation for use of the DILG Personnel (RAT) during the SGLG Assessment on July 05, 2023, Bato, Leyte | [9 empty] | 2023-06-30 |  |  | 2023-07-04 | 2023-07-04 |  | 1410 |  |  | 1237.11
Purchase of Spare Parts for use in the Repair of LGU Dumptruck, Bato, Leyte
| Purchase of various Construction Supplies for use in the Fabrication of Full Disclosure Policy Board, LGU, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-13 | 2023-07-13 |  | 25010 |  |  | 24940
| Supplies for use as Giveaways during the Awarding of Top Barangays in connection with the Voluntary Blood Donation Program of the Municipality of Bato, Leyte on July 17, 2023. | [9 empty] | 2023-07-10 |  |  | 2023-07-14 | 2023-07-14 |  | 4130 |  |  | 4130
| Purchase of various materials for use in the Installation of RC Pipe along Barangay Amagos Road, Bato, Leyte | [9 empty] | 2023-07-11 |  |  | 2023-07-13 | 2023-07-13 |  | 93100 |  |  | 93100
| Meal for use during the Opening Salvo (Barbecue Festival) in connection with the Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-07-11 |  |  | 2023-07-17 | 2023-07-17 |  | 52500 |  |  | 52500
| Sound System Service and LED Wall for use during the Opening Salvo (Barbecue Festival) in connection with the Socio-Cultural Activities held at Bato, Leyte | [9 empty] | 2023-07-11 |  |  | 2023-07-17 | 2023-07-17 |  | 75000 |  |  | 65000
| To Provide Meals for the upcoming Joint Parish and LGU Founding Anniversary in connection with socio- cultural activities of LGU- Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | June 28- July 18, 2023 |  | July 18, 2023 | July 18, 2023 | July 19, 2023 | July 19-20, 2023 | July 21, 2023 | July 21-24, 2023 | July 25, 2023 | July 27, 2023 | July 27, 2023 | Socio- Cultural | 178400 | 178400 |  | 178400 | 178400 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 18, 2023 | July 18, 2023 | July 19, 2023 | July 19-20, 2023 | July 27, 2023 | Completed
| Improvement of MDRRMO Operation Center, Brgy. Bagongbayan, Bato, Leyte | MDDRMO/ Atty. Louie W. Suico | Public Bidding |  | July 5-27, 2023 |  | July 27,2023 | July 27,2023 | July 28, 2023 | July 31- August 2, 2023 | August 4, 2023 | August 7-8, 2023 | August 9, 2023 |  |  | TF/ MDRRM | 1227427.36 |  | 1227427.36 | 1226426.98 |  | 1226426.98 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 27,2023 | July 27,2023 | July 28, 2023 | July 31- August 2, 2023 |  | Completed
| Backfilling of Iniguihan Reclamation, Brgy. Iniguihan, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | July 6-28, 2023 |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-31, 2023 | August 4, 2023 | August 8-9, 2023 | August 10, 2023 | November 21, 2023 | November 13, 14,15,16,17, 18, 20 & 21, 2023 | General Fund- 20% Development Fund | 4999071.84 | 4999071.84 |  | 4998068.1 | 4998068.1 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-31, 2023 | November 21, 2023 | Completed
| Construction of Drainage Canal, Brgy. Iniguihan, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | July 6-28, 2023 |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-3, 2023 | August 4, 2023 | August 8-9, 2023 | August 10, 2023 |  |  | General Fund 20% Development Fund | 1049120.1 | 1049120.1 |  | 1048119.85 | 1048119.85 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-3, 2023
| Completion Barangay Gym, Brgy. Domagocdoc, Bato, leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | July 10-31, 2023 |  | July 31, 2023 | July 31, 2023 | August 1, 2023 | August 2-4, 2023 | August 8, 2023 | August 10-11, 2023 | August 14, 2023 | November 22, 2023 |  | General Fund 20% Development Fund | 2204488.44 |  | 2204488.44 | 2203486.5 |  | 2203486.5 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 31, 2023 | July 31, 2023 | August 1, 2023 | August 2-4, 2023 | November 22, 2023 | Completed
| Enhancement and Updating of LDRRM (Local Disaster Risk Reduction and Management ) Plan for 2023 to 2025 | MDDRMO/ Atty. Louie W. Suico | Public Bidding |  | July 6-28, 2023 |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-3, 2023 | August 4, 2023 | August 8, 2023 | August 10, 2023 | August 17, 2023 | August 15, 16 & 17, 2023 | 5% MDRRM Fund | 357000 | 357000 |  | 357000 | 357000 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 28, 2023 | July 28, 2023 | July 31, 2023 | August 1-3, 2023 | August 17, 2023 | Completed
| Purchase of various Construction Supplies for use in the Installation of Pegeon Hall, Signages and Tile Reinstallation in the OSCA Office, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-13 | 2023-07-13 |  | 6140 |  |  | 6140
| Tarpaulin Printing for use of the General Program of Activities during the 137th Joint Parish and Municipal Founding Anniversary, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-17 | 2023-07-17 |  | 1950 |  |  | 1800
| Table Rental for use during the 137th Joint Parish and Municipal Founding Anniversary 2023, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-17 | 2023-07-17 |  | 1500 |  |  | 1200
| Tent Rental for use during the 137th Joint Parish and Municipal Founding Anniversary 2023, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-17 | 2023-07-17 |  | 40000 |  |  | 40000
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity held at Holy Child Covered Court, Brgy. Bagongbayan Bato, Leyte on July 23, 2023 and Brgy. Tabunok, Bato, Leyte on August 03, 2023 | [9 empty] | 2023-07-17 |  |  | 2023-07-20 | 2023-07-20 |  | 29450 |  |  | 27060
| Meal and Snacks for use during the 2023 Voluntary Blood Donation Activity at Holy Child Covered Court, Brgy. Bagongbayan, Bato, Leyte on July 23, 2023 | [9 empty] | 2023-07-17 |  |  | 2023-07-23 | 2023-07-23 |  | 17500 |  |  | 17500
| Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Holy Child Covered Court, Brgy. Bagongbayan Bato, Leyte on July 23, 2023 and Brgy. Tabunok, Bato, Leyte on August 03, 2023 | [9 empty] | 2023-07-17 |  |  | 2023-07-20 | 2023-07-20 |  | 2000 |  |  | 2000
| Sound System Service and LED Wall for use during the Joint Parish and LGU Founding Anniversary in connection with the Socio-Cultural Activities in Bato, Leyte | [9 empty] | 2023-07-18 |  |  | 2023-07-26 | 2023-07-26 |  | 75000 |  |  | 65000
Purchase of various Agricultural Supplies for use in the Municipal Agriculture Office, LGU, Bato, Leyte
| Purchase of Office Supplies for use in the Bids and Awards Committee (BAC) Office, Bato, Leyte | [9 empty] | 2023-07-18 |  |  | 2023-07-20 | 2023-07-20 |  | 16878.4 |  |  | 16796
| Purchase of Jetmatic Pump and Laminated Sack for use in the Water System for Plaridel Farmers Association (PLARFA), Brgy. Plaridel, Bato, Leyte and Brgy. Cebuana, Bato, Leyte | [9 empty] | 2023-07-18 |  |  | 2023-07-27 | 2023-07-27 |  | 16750 |  |  | 16750
| Purchase of Various Construction Supplies for use in the Repair of the Children Playground at Bato Baywalk, Bato, Leyte | [9 empty] | 2023-07-18 |  |  | 2023-07-25 | 2023-07-25 |  | 30510 |  |  | 30010
| Meal and Snacks for use during the Municipal Development Council Meeting on July 14, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-07-10 |  |  | 2023-07-16 | 2023-07-16 |  | 18000 |  |  | 18000
4 unit Dumptruck
| Purchase of Office Equipment for MDRRM Weather and Traffic Monitoring and 24/7 Operation, MDRRM Office, LGU- Bato, Leyte | MDDRMO/ Atty. Louie W. Suico | Public Bidding |  | July 24- August 14, 2023 |  | August 14, 2023 | August 14, 2023 | August 15, 2023 | August 22, 2023 | August 24, 2023 | August 28-29, 2023 | August 30, 2023 | September 5, 2023 | September 5, 2024 | Special Trust Fund- DRRMF | 240000 |  | 240000 | 240000 |  | 240000 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | August 14, 2023 | August 14, 2023 | August 15, 2023 | August 22, 2023 | September 5, 2023 | Completed
| Purchase of Laboratory Supplies for use in the Bato Diagnostic Center, Bato, Leyte | [9 empty] | 2023-07-17 |  |  | 2023-07-20 | 2023-07-20 |  | 38500 |  |  | 38500
| Purchase of Laboratory Supplies for use in the Bato Diagnostic Center, Bato, Leyte | [9 empty] | 2023-07-17 |  |  | 2023-07-20 | 2023-07-20 |  | 100000 |  |  | 7500
| Purchase of various materials for use in the Repair of Interlink Fence of LGU, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-31 | 2023-07-31 |  | 100000 |  |  | 99630
| Purchase of Mixed Sand and Gravel for use in the Resurfacing of Sitio Caragasan, Brgy. Amagos, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-27 | 2023-07-27 |  | 100000 |  |  | 100000
| Snacks for use during the 2023 Nutrition Month Celebration Activities (Nutrition Quiz and Cooking Contest), Bato, Leyte | [9 empty] | 2023-07-24 |  |  | 2023-07-27 | 2023-07-27 |  | 7000 |  |  | 7000
| Tarpaulin Printing and Balloons for use during the 2023 Nutrition Month Celebration Culmination Program, Bato, Leyte | [9 empty] | 2023-07-24 |  |  | 2023-07-26 | 2023-07-26 |  | 3644 |  |  | 3584
Tarpaulin Printing for use in the MDRRM Operation Center, Bato, Leyte
| Purchase of Steel Plate and Welding Rod for use in the Repair of the LGU Payloader, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-28 | 2023-07-28 |  | 16300 |  |  | 16200
| Purchase of Oil and Lubricants for use in the Repair and Maintenance of the LGU Dumptruck, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-28 | 2023-07-28 |  | 7360 |  |  | 7360
| Purchase of Office Supplies for use in the Municipal Budget Office, LGU, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-08-01 | 2023-08-01 |  | 16733 |  |  | 16733
| Purchase of Supplies for use the Drone Camera of LGU, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-31 | 2023-07-31 |  | 24405 |  |  | 24405
| Purchase of Mixed Sand and Gravel for use in Patching of Potholes at Kalanggaman Reclamation, Bus Terminal Bound for Bohol and Manila, Brgy. Kalanggaman, Bato, Leyte | [9 empty] | 2023-07-27 |  |  | 2023-07-31 | 2023-07-31 |  | 100000 |  |  | 100000
| Purchase of Various Medical Supplies for Maternal and Child Health Program in the Municipal Health Office, LGU, Bato, Leyte | [9 empty] | 2023-07-27 |  |  | 2023-08-04 | 2023-08-04 |  | 73188.8 |  |  | 69770
| Snacks for use during the Orientation of Barangay Development Plan (BDP) on July 31, 2023, Bato, Leyte | [9 empty] | 2023-07-25 |  |  | 2023-07-31 | 2023-07-31 |  | 7500 |  |  | 7500
| T-Shirt with Print for use during the Municipal Agriculture Office, Farmers Field School (FFS) Graduation in Brgy. Liberty and Brgy. Bago, Bato, Leyte on August 10 and 22, 2023 | [9 empty] | 2023-07-31 |  |  | 2023-08-08 | 2023-08-08 |  | 23200 |  |  | 23200
| Purchase of various Materials for use in the Lightings of Public Market Building (Wet Market), Slaughter House, and MRF Building, Bato, Leyte | [9 empty] | 2023-07-31 |  |  | 2023-08-08 | 2023-08-08 |  | 48610 |  |  | 48340
| Purchase of Mixed Sand and Gravel for use in Patching of Potholes at Barangay Road to Dumpsite, Brgy. Ponong, Bato, Leyte | [9 empty] | 2023-08-03 |  |  | 2023-08-07 | 2023-08-07 |  | 100000 |  |  | 100000
| Purchase of Various Hardware Materials for use in the Maintenance of the Municipal Hall, Bato, Leyte | [9 empty] | 2023-08-03 |  |  | 2023-08-08 | 2023-08-08 |  | 99300 |  |  | 99160
Purchase of Diesel for use in the Consumption of LGU Ambulance in Getting Vaccines and Family Planning Commodities at the Provincial Health Office, Palo, Leyte on August 03, 2023
Purchase of Gasoline for use in the Consumption of LGU Sea Ambulance during the Monthly Consultation, Health Awareness and Operation Tuli at Brgy. Dawahon, Bato, Leyte
| Cleaning Services for the Maintenance of the Photocopier use in the Accounting Office, Bato, Leyte | [9 empty] | 2023-08-07 |  |  | 2023-08-09 | 2023-08-09 |  | 1600 |  |  | 1550
| Purchase of Portland Cement for use in the Drainage Culvert at Sitio Talisayan, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-08-07 |  |  | 2023-08-09 | 2023-08-09 |  | 4950 |  |  | 4950
| Tarpaulin Printing for use in the Information Education Communication (IEC) for Solid Waste Management, Bato, Leyte | [9 empty] | 2023-08-07 |  |  | 2023-08-10 | 2023-08-10 |  | 2988 |  |  | 2988
| Meals and Snacks for use during the Farmers Field School (FFS) Graduation in Brgy. Liberty, Bato, Leyte on August 10, 2023 and in Brgy. Bago, Bato, Leyte on August 22, 2023 | [9 empty] | 2023-08-07 |  |  | 8/10 & 22/2023 | 8/10 & 22/2023 |  | 33000 |  |  | 33000
| Purchase of various Automotive Supplies for use in Changing Oil of LGU Ambulance, Bato, Leyte | [9 empty] | 2023-08-08 |  |  | 2023-08-10 | 2023-08-10 |  | 9720 |  |  | 9720
| Procurement of Fuel for the Construction of Mabini Spillway, Brgy. Mabini, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | June 22- July 12, 2023 |  | July 12, 2023 | July 12, 2023 | July 13, 2023 | July 18-14, 2023 | July 20, 2023 | July 24-25, 2023 | July 26, 2023 |  |  | Genaral Fund- 20% Development Fund | 440000 |  | 440000 | 440000 |  | 440000 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | July 12, 2023 | July 12, 2023 | July 13, 2023 | July 18-14, 2023 |  | Completed
| Purchase of various Office Supplies for use during the Enhancement and Updating of LDRRM Plan for 2023 to 2025, Bato, Leyte | [9 empty] | 2023-08-08 |  |  | 2023-08-10 | 2023-08-10 |  | 13710 |  |  | 12931
| Purchase of supplies and Tarpaulin Printing for use during the Enhancement and Updating of LDRRM Plan for 2023 to 2025, Bato, Leyte | [9 empty] | 2023-08-09 |  |  | 2023-08-11 | 2023-08-11 |  | 3595 |  |  | 3426
| Meal and Snacks for use during the Joint Meeting of Provincial Agriculture & Fishery Council and MAF; and Mangrove Planting in Brgy. Dawahon, Bato, Leyte on August 18, 2023 | [9 empty] | 2023-08-10 |  |  | 2023-08-18 | 2023-08-18 |  | 54000 |  |  | 54000
Purchase of Diesel for use during the Joint Meeting of the Provincial Agricultural and Fishery Council and MAFC and Mangrove Planting in Brgy. Dawahon, Bato, Leyte on August 18, 2023
| Purchase of Powder Bio-enzymes for use in Closed Dumping Facility, Central Material Recovery Facility and General Usage in Solid Waste Management, Bato, Leyte | [9 empty] | 2023-08-14 |  |  | 2023-08-23 | 2023-08-23 |  | 25000 |  |  | 25000
| Purchase of Office Supplies for use in the Human Resource and Management Office, Bato, Leyte | [9 empty] | 2023-08-14 |  |  | 2023-08-23 | 2023-08-23 |  | 4500 |  |  | 4350
Purchase of Office Supplies for use in the Municipal Treasurer's Office, Bato, Leyte
| Purchase of Various Materials for use in the Repair of the Children's Playground, Bato Baywalk, Bato, Leyte | [9 empty] | 2023-08-14 |  |  | 2023-08-16 | 2023-08-16 |  | 14303 |  |  | 14210
| Purchase of Tire & Spare Part for LGU Tractor (YTO X904) for use in the Municipality of Bato, Leyte | Municipal Agrriculture Office/ Engr. Danilo D. Germano | Public Bidding |  | August 29- September 19, 2023 |  | September 19, 2023 | September 19, 2023 | September 20, 2023 | September 21-22, 2023 | September 26, 2023 | September 29, 2023 | October 2, 2023 | October 10, 2023 | October 10, 2023 | General Fund | 142660 | 142660 |  | 140200 | 140200 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | September 19, 2023 | September 19, 2023 | September 20, 2023 | September 21-22, 2023 | October 10, 2023 | Completed
| Purchase of Various Materials for the Improvement and Repainting of Different School Amenties in the Bato East District, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | September 11- October 2, 2023 |  | October 2,2023 | October 2, 2023 | October 3, 2023 | October 4-6, 2023 | October 9, 2023 | October 12, 2023 | October 13, 2023 | October 11, 2023 | October 11, 2024 | SEF | 103398 | 103398 |  | 103289 | 103289 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | October 2,2023 | October 2, 2023 | October 3, 2023 | October 4-6, 2023 | October 11, 2024 | Completed
| Tarpaulin Printing for use in the Environmental Sanitation IEC, Family Planning, National Breastfeeding and National Lung Month, Bato, Leyte | [9 empty] | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 |  | 2800 |  |  | 2760
| Snacks for use during the Buntis Congress 2023 in connection with the National Breastfeeding and Family Planning Month, Bato, Leyte | [9 empty] | 2023-08-23 |  |  | 2023-08-30 | 2023-08-30 |  | 5000 |  |  | 5000
Purchase of Various Medical Supplies for use in the Buntis Congress 2023 In Connection with the National Breastfeeding and Family Planning Month, Bato, Leyte
| Purchase of Various Materials for use in the Drainage Concrete Cover (Existing Drainage), Bato, Leyte | [9 empty] | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 |  | 36175 |  |  | 36100
Purchase of Office Supplies for use in the Drug Clearing Activity of the Municipality of Bato, Leyte
| Purchase of School and Office Supplies for use of the Different Schools in the Bato East District, Bato, Leyte | [9 empty] | 2023-08-30 |  |  | 2023-09-05 | 2023-09-05 |  | 15000 |  |  | 10065
| Purchase of PE Hose for use in the Water System of Brgy. Cebuana, Bato, Leyte | [9 empty] | 2023-08-30 |  |  | 2023-09-07 | 2023-09-07 |  | 5600 |  |  | 5600
Purchase of Computer Desktop for use in Bato East District Office, Bato, Leyte
| Purchase of Various Materials for use in the Rehabilitation of 2-Units Makeshift Building of Buli National High School, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-08-31 |  |  | 2023-09-08 | 2023-09-08 |  | 65100 |  |  | 65005
| Purchase of Various Materials for use in the Repair of BATO LEYTE Signage at Bato Baywalk, Brgy. Kalanggaman, Bato, Leyte | [9 empty] | 2023-08-31 |  |  | 2023-09-07 | 2023-09-07 |  | 100000 |  |  | 99500
| Purchase of various Agricultural Supplies for use in the Municipal Agriculture Office, LGU, Bato, Leyte | [9 empty] | 2023-08-31 |  |  | 2023-09-06 | 2023-09-06 |  | 99710 |  |  | 99704
Purchase of Various Materials for use in the On-going Construction of the Makeshift Building in Marcelo Elementary School, Brgy. Marcelo, Bato, Leyte
| Purchase of Various Materials for use in the Rehabilitation of Bato Port Causeway and Preventive Maintenance of Tower Base at Bato Port, Bato, Leyte | [9 empty] | 2023-09-04 |  |  | 2023-09-07 | 2023-09-07 |  | 39640 |  |  | 39360
Purchase of Various Materials for use in the Improvement of Comfort Room at Buli Elementary School, Brgy. Buli, Bato, Leyte
| Meals and Snacks for use during the System Installation, Orientation and Data Build-Up of iTax System, Bato, Leyte | [9 empty] | 2023-08-30 |  |  | 9/5/2023 & 9/6/23 | 9/5/2023 & 9/6/23 |  | 26000 |  |  | 36000
| Room Accommodation for use of the PASSO and PTO Personnel during the System Installation, Orientation and Data Build-Up of iTax System, Bato, Leyte | [9 empty] | 2023-08-30 |  |  | 2023-09-05 | 2023-09-05 |  | 2000 |  |  | 2000
| Meal and Snacks for use during the Payout of the Educational Assistance on September 07, 2023, Bato, Leyte | [9 empty] | 2023-09-04 |  |  | 2023-09-07 | 2023-09-07 |  | 5250 |  |  | 5250
| Meals and Snacks for use during the Spray Paint Technique Training for Badjao Community, Bato, Leyte | [9 empty] | 2023-09-04 |  |  | 2023-09-07 | 2023-09-07 |  | 32000 |  |  | 32000
Tarpaulin Printing for use in the Celebration of the 123rd Philippine Civil Service Anniversary, September 2023, Bato, Leyte
Purchase of Various Materials for use in the Improvement of Comfort Rooms (Floor and Wall Tiling) near BSFMPC Building at Bato School of Fisheries, Bato, Leyte
Purchase of Toner for use of the Photocopier in the Office of the Mayor and BAC Office, LGU, Bato, Leyte
Purchase of Gasoline for use in the Consumption of LGU Sea Ambulance during the Monthly Consultation, Health Awareness at Brgy. Dawahon, Bato, Leyte
Purchase of Construction Materials for use as Assistance for the House Fire Victims in Brgy. Osmeña, Bato, Leyte
Purchase of Various Materials for use in the SMAW Laboratory in Bato National High School, Bato, Leyte
Purchase of Solar Lights for use as Lightings to be Installed in the School Buildings, Bato National High School, Bato, Leyte
Maintenance of Air-Conditioning Unit for use in the Office of the Municipal Accountant, LGU, Bato, Leyte
| Purchase of Various Supplies and Materials for use as Promotional Give-aways for Tourism Program/Activities, LGU, Bato, Leyte | [9 empty] | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 |  | 30000 |  |  | 29680
| Meal and Snacks for use during the Budget Hearing on September 15, 2023, 3rd Floor Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-09-11 |  |  | 2023-09-15 | 2023-09-15 |  | 17500 |  |  | 17500
Purchase of Supplies and Equipment for use during the Friendly Games in connection with the 123rd Civil Service Anniversary Celebration, Bato, Leyte
Purchase of Various Materials for use in the Rehabilitation of Drainage Cover along Juan Luna St. Poblacion, Bato, Leyte
Purchase of Industrial Acetelyn and Industrial Oxygen for use in the LGU Motorpool, Bato, Leyte
Purchase of Supplies and Materials for use in the Water System of Barangay Guerrero, Bato, Leyte
| Meal and Snacks for use during the 123rd Civil Service Anniversary on September 22, 2023 held at Bato School of Fisheries, Bato, Leyte | [9 empty] | 2023-09-14 |  |  | 2023-09-22 | 2023-09-22 |  | 95400 |  |  | 95400
| Meal and Snacks for use during the Alay Lakad 2023 Celebration held on September 22, 2023 at Brgy. Tabunok, Bato, Leyte | [9 empty] | 2023-09-14 |  |  | 2023-09-22 | 2023-09-22 |  | 55650 |  |  | 55650
Purchase of Mixed Sand and Gravel for use in Resurfacing of Barangay Road at Sitio Ponod, Brgy. Tabunok, Bato, Leyte
Purchase of Mixed Sand and Gravel for use in Resurfacing of Barangay Road at Sitio Can-idlang, Brgy. Tabunok, Bato, Leyte
Purchase of Mixed Sand and Gravel for use in Backfilling at Bagongbayan Evacuation Center, Brgy. Bagongbayan, Bato, Leyte
Purchase of Mixed Sand and Gravel for use in Patching of Potholes at Barangay Road to Dumpsite, Brgy. Ponong, Bato, Leyte
| Completion of Mini Gym, Sitio Amagos II, Brgy. Amagos, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | August 29- September 19, 2023 |  | September 19, 2023 | September 19, 2023 | September 20, 2023 | September 21-22, 2023 | September 26, 2023 | September 28-29, 2023 | October 2, 2023 | November 28, 2023 |  | 20% Development Fund0 | 1040413.5 |  | 1040413.5 | 1039413.69 |  | 1039413.69 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | September 19, 2023 | September 19, 2023 | September 20, 2023 | September 21-22, 2023 | November 28, 2023 | Completed
Purchase of Office Supplies for use in the Municipal Accounting Office, LGU, Bato, Leyte
Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity at Brgy. Buli, Bato, Leyte on Sept. 22, 2023 and Brgy. Tagaytay, Bato, Leyte on Sept. 29, 2023
Meal and Snacks for use during the 2023 Voluntary Blood Donation Activity at Brgy. Buli, Bato, Leyte on Sept. 22, 2023
Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity held at Brgy. Buli, Bato, Leyte on Sept. 22, 2023 and Brgy. Tagaytay, Bato, Leyte on Sept. 29, 2023
Purchase of Solar Panel Set for use in Dawahon Integrated School - JHS, Brgy. Dawahon, Bato, Leyte
Various Materials bato east
Purchase of Various Materials for use in the Construction of Agriculture Building of Bato Central School, Brgy. Kalanggaman, Bato, Leyte
Tent Rental for use during the Alay Lakad 2023 Celebration on September 22, 2023 at Brgy. Tabunok, Bato, Leyte
Purchase of Electrical Supplies for use in the Childred Playground at Bato Baywalk, Bato, Leyte
Tarpaulin Printing for use during the Awarding of Check (DSWD-SLP), Bato, Leyte
Brochure Printing and Layout Services for use in the Municipal Civil Registrar Office, Bato, Leyte
Room Accommodation for use of the PSA Personnel conducting Survey to Six (6) Barangays, Bato, Leyte
Purchase of Diesel for use in the Consumption of LGU Ambulance In Getting Flu Vaccines, Routine Vaccines and Family Planning Commodities at the Provincial Health Office, Palo, Leyte
Purchase of Office Supplies for use in the Municipal Treasurer's Office, Bato, Leyte
Purchase of Diesel for use in the Consumption of LGU Service Vehicle to Deposit Municipal Collection and Encash Checks for Salaries and Wages and Other Official Business Transaction at Maasin City, Tacloban City and Baybay City
| Purchase of Signage and Accessories for use in the Municipal Treasurer's Office, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | September 27- October 17, 2023 |  | October 17, 2023 | October 17, 2023 | October 18, 2023 | October 18-19, 2023 | October 24, 2023 | October 27, 2023 | October 31, 2023 |  |  | General Fund | 250000 | 250000 |  | 249800 | 249800 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | October 17, 2023 | October 17, 2023 | October 18, 2023 | October 18-19, 2023
Meal and Snacks for use during the DSWD Bagong Pilipinas AICS Payout on October 05, 2023, Bato, Leyte
| Tarpaulin Printing for use during the Awarding of Check for DOLE Livelihood and An Waray Party List Payout, Bato, Leyte | [9 empty] | 2023-09-29 |  |  | 2023-10-03 | 2023-10-03 |  | 750 |  |  | 620
Snacks for use during the Orientation for KALAHI-CIDSS AF DROM on October 05, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte
Purchase of Hematology Reagent for use in the Bato Diagnostic Center, Bato, Leyte
| Rehabilitation of Flood Control (Phase 1), Brgy. Iniguihan, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | September 20- October 11, 2023 |  | October 11, 2023 | October 11, 2023 | October 12, 2023 | October 13-17, 2023 | October 19, 2023 | October 23-24, 2023 | October 25, 2023 |  |  | Special Trust Fund/ DRRMF | 5000000 | 5000000 |  | 4994990.87 | 4994990.87 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | October 11, 2023 | October 11, 2023 | October 12, 2023 | October 13-17, 2023
Purchase of Gasoline for use in the Consumption of LGU Sea Ambulance during the Monthly Consultation, Health Awareness at Brgy. Dawahon, Bato, Leyte
Purchase of Construction Supplies for use in the Maintenance of the Evacuation Center, Bato, Leyte
Purchase of Construction Supplies for use in the Signage at Bato Baywalk Ground, Bato, Leyte
Meals and Snacks for use during the Logistics Management Training (Transportation & Warehousing) on October 10-11, 2023 at the Municipal Function Hall, Bato, Leyte
Purchase of Plumbing Materials for use in the Supply of Water from Ground Floor to Third Floor of the Municipal Hall Building, LGU, Bato, Leyte
Purchase of Christmas Lantern with LED Lights for use as Christmas Decoration in the Municipal Hall Building, LGU, Bato, Leyte
Maintenance of Air-Conditioning Unit for use in the Office of the Municipal Engineer, LGU, Bato, Leyte
| Backfilling of Iniguihan Reclamation, Brgy. Iniguihan, Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | October 9-30, 2023 |  | October 31, 2023 | October 31, 2023 | October 31, 2023 | November 3-6, 2023 | November 7, 2023 | November 9-10, 2023 | November 13, 2023 |  |  | General Fund/ 20% Development Fund | 1962550 |  | 1962550 | 1962536 |  | 1962536 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | October 31, 2023 | October 31, 2023 | October 31, 2023 | November 3-6, 2023
| Purchase of Office Supplies for use in the Office of the Municipal Mayor, Bato, Leyte | [9 empty] | 2023-10-16 |  |  | 2023-10-24 | 2023-10-24 |  | 8470 |  |  | 8470
| Procurement of Various Medicines for TB Program, Rural Health Unit, Bato, Leyte | Rural Health Unit/ Dr. Probo P. Quijano | Public Bidding |  | October 11- November 3, 2023 |  | November 3, 2023 | November 3, 2023 | November 6, 2023 | November 7-9, 2023 | November 13, 2023 | November 15-16, 2023 | November 17, 2023 | November 29, 2023 | November 29, 2024 | General Fund | 149800 | 149800 |  | 146500 | 146500 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | November 3, 2023 | November 3, 2023 | November 6, 2023 | November 7-9, 2023 | November 29, 2023 | Completed
| Purchase of Various Office Supplies amd Consumables for the 10 schools of the Bato West District of Bato, Leyte | Municipal Mayor / Hon. Nataniel B. Gertos | Public Bidding |  | October 11- November 3, 2023 |  | November 3, 2023 | November 3, 2023 | November 6, 2023 | November 7-9, 2023 | November 13, 2023 | November 16, 2023 | November 17, 2023 | November 29, 2023 & December 1, 2023 | November 29, 2023 & December 1, 2023 | General Fund SEF | 128400 | 128400 |  | 128380 | 128380 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | November 3, 2023 | November 3, 2023 | November 6, 2023 | November 7-9, 2023 | November 29, 2023 & December 1, 2023 | Completed
Meal and Snacks for use during the TUPAD Payout through An Waray Party List and Assistance to Individual in Crisis Situation (AICS) Payout on October 18, 2023, Bato, Leyte
| Purchase of Office Supplies for use in Bato National High School, Bato, Leyte | [9 empty] | 2023-10-16 |  |  | 2023-10-24 | 2023-10-24 |  | 10000 |  |  | 10000
Purchase of Tire Wheel for use in the Mini Dumptruck of LGU, Bato, Leyte
BFP Supplies
Purchase of Sublimation T-shirt for use during the Voluntary Blood Donation, Bato, Leyte
Purchase of Various Automotive Supplies for use in Changing Oil of RHU Ambulance (Nissan Urvan 350 NV), PNP Toyota Patrol Van and Rescue Vehicle (Nissan Navara), Bato, Leyte
Purchase of Various Automotive Supplies for use in the Repair and Checking Water Pump Pressure of Fire Truck, Bato, Leyte
| Resurfacing of Road to Dumpsite, Brgy. Ponong, Bato, Leyte | Municipal Mayor/ Hon. Nathaniel B. Gertos | Public Bidding |  | October 18- November 7, 2023 |  | November 7, 2023 | November 7, 2023 | November 8, 2023 | November 9-13, 2023 | November 15, 2023 | November 20, 2023 | November 21, 2023 | December 2, 2023 | November 30, December 1 & December 2, 2023 |  | 657550 | 657550 |  | 657536 | 657536 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | November 7, 2023 | November 7, 2023 | November 8, 2023 | November 9-13, 2023 | November 30, December 1 & December 2, 2023
| Purchase of various Electrical Supplies for use in the Street Lighting at Mabini St., and Jacinto St., Bato, Leyte | [9 empty] | 2023-10-16 |  |  | 2023-11-03 | 2023-11-03 |  | 66250 |  |  | 66250
Meals and Snacks for use during the Social Pension Payout for the Senior Citizens' on November 06 - 10, 2023 at Bato, Leyte
| Procurement of Seeds for the cropping season from November to April 2023 for Rice and July to December for Corn | Municipal Agrriculture Office/ Engr. Danilo D. Germano | Public Bidding |  | November 14- December 5, 2023 |  | December 5, 2023 | December 5, 2023 | December 6, 2023 | December 7-8, 2023 | December 12, 2023 | December 14-15, 2023 | December 18, 2023 |  |  | General Fund | 1163850 | 1163850 |  | 1163200 | 1163200 |  | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | December 5, 2023 | December 5, 2023 | December 6, 2023 | December 7-8, 2023 |  | Completed
Meals and Snacks for use during the Distribution and Receipt of Ballot Boxes in connection with the Barangay and SK Elections 2023, Bato, Leyte
| Purchase of Office Supplies for use in Senior Citizen Social Pension Payout, 2nd Semester of CY 2023, Bato, Leyte | [9 empty] | 2023-10-31 |  |  | 2023-11-06 | 2023-11-06 |  | 8962 |  |  | 8962
| Purchase of Office Supplies for use in the Office of the Municipal Engineer, LGU, Bato, Leyte | [9 empty] | 2023-10-31 |  |  | 2023-11-09 | 2023-11-09 |  | 23926 |  |  | 23926
Surveying Services (Subdivision Survey) of Lot # 1663-A-1-E at Barangay Tabunok, Bato, Leyte as LGU Documentation
| Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity on Nov. 08, 2023 at Brgy. Tabunok, Bato, Leyte | [9 empty] | 2023-10-31 |  |  | 2023-11-06 | 2023-11-06 |  | 15350 |  |  | 14320
Tarpaulin Printing for use during the 2023 Voluntary Blood Donation Activity on Nov. 08, 2023 at Brgy. Tabunok, Bato, Leyte
| Meals and Snacks for use during the Payout of Emergency Cash Transfer (ECT) for Typhoon Paeng, Bato, Leyte | [9 empty] | 2023-11-07 |  |  | 11/10 and 11/11 | 11/10 and 11/11 |  | 31500 |  |  | 31500
Purchase of Collapsible Tent for use in Outdoor School Activities and Programs at Bato National High School, Bato, Leyte
| Meals and Snacks for use during the Training for Biosecurity for Swine on November 16-17, 2023 at the 3rd Floor, Municipal Hall Building, Bato, Leyte | [9 empty] | 2023-11-13 |  |  | 11/16 and 11/17 | 11/16 and 11/17 |  | 29400 |  |  | 29400
| Purchase of Materials for use in the Fabrication of BFAR Pump Boat as LGU Counterpart, Bato, Leyte | [9 empty] | 2023-11-13 |  |  | 2023-11-16 | 2023-11-16 |  | 28800 |  |  | 28800
| Meals and Snacks for use during the Orientation and Election of the Pambayang Pederasyon ng mga Sangguniang Kabataan held on Nov. 13, 2023, Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-11-10 |  |  | 2023-11-13 | 2023-11-13 |  | 16100 |  |  | 16100
| Purchase of Luna-Trapal for use in Replacement/Augmentation of the Worn Trapal for Bato Port Operations, Bato, Leyte | [9 empty] | 2023-11-16 |  |  | 2023-11-21 | 2023-11-21 |  | 77500 |  |  | 77500
Meal and Snacks for use during the Project Development Workshop (PDW), KALAHI-CIDSS NCDDP AF DROM on November 20, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte
Purchase of Portland Cement for use in Concreting of School Pathway at Osmeña Elementary School, Brgy. Osmeña, Bato, Leyte
Purchase of Various Materials for use in the Repair of Grade 1 & 2 Classroom of Domagocdoc Primary School, Brgy. Domagocdoc, Bato, Leyte
Purchase of Tire Wheel for use in the RHU Nissan Urban NV 350 Ambulance of LGU, Bato, Leyte
| MDRRM Rescue Equipment | [12 empty] | December 20, 2023 | December 20, 2023 | [13 empty] | December 20, 2023
| Purchase of Supplies and Materials for use in the Maintenance of the RHU Generator, LGU, Bato, Leyte | [9 empty] | 2023-11-20 |  |  | 2023-11-28 | 2023-11-28 |  | 22250 |  |  | 21950
| Purchase of Supplies and Materials for use in Early Warning System of the MDRRMO Operation Center, Bato, Leyte | [9 empty] | 2023-12-04 |  |  | 2023-12-12 | 2023-12-12 |  | 98058 |  |  | 97900
| Purchase of Fusing Unit Dcs 2320 for use in the Replacement of the Defective Roller of the Photocopier at Bato West District Office, Bato, Leyte | [9 empty] | 2023-12-05 |  |  | 2023-12-13 | 2023-12-13 |  | 15600 |  |  | 15600
| Meal and Snacks for use during the Municipal Development Council (MDC) Meeting on November 29, 2023 at the Function Hall, Balay Lungsod, Bato, Leyte | [9 empty] | 2023-11-20 |  |  | 2023-11-29 | 2023-11-29 |  | 21000 |  |  | 21000
| T-shirt with Print for use during the MAO Farmers Field School (FFS) Graduation for Vegetables on December 12, 2023 in Sitio Talisayan, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-12-05 |  |  | 2023-12-12 | 2023-12-12 |  | 16600 |  |  | 16600
| Meal and Snacks for use during the Farmers Field School (FFS) Graduation for Vegetables on December 12, 2023 in Sitio Talisayan, Brgy. Buli, Bato, Leyte | [9 empty] | 2023-12-05 |  |  | 2023-12-12 | 2023-12-12 |  | 27000 |  |  | 27000
T-shirt with Print for use during the MAO Farmers Field School (FFS) Graduation for Corn on December 14, 2023 in Brgy. Sto. Niño, Bato, Leyte
| Meal and Snacks for use during the Farmers Field School (FFS) Graduation for Corn on December 14, 2023 in Brgy. Sto. Niño, Bato, Leyte | [9 empty] | 2023-12-05 |  |  | 2023-12-14 | 2023-12-14 |  | 30000 |  |  | 30000
Purchase of Roofing Materials for use in Replacement of Rotten GI Roofing Sheet in the Gabaldon School, Building, Bato, Leyte
Purchase of Construction Materials for use in the Repair of Meat Processing (Boiling Water) at the Slaughterhouse, Brgy. Iniguihan, Bato, Leyte
Meat Products DOLE
Feeds DOLE
Purchase of Vellum Board for use in Environmental Sanitation IEC, Bato, Leyte
Metal Interlink
Purchase of Construction Materials for use in the Improvement of Public Comfort Room (Old Wet Market) Brgy. Iniguihan, Bato, Leyte
Purchase of Supplies and Materials for use in the Repair of LGU Garbage Truck (Dumpbox Flooring), Bato, Leyte
Purchase of Plumbing Materials for use in the Improvement of Water System in Bato Baywalk Comfort Rooms, Brgy. Kalanggaman, Bato, Leyte
Purchase of various Frozen Foods for use in the DOLE Livelihood Program (DILP) for the Livelihood Project for the Parent of Child Laborers in the Municipality of Bato, Leyte
Purchase of Various Materials for use in DOLE Integrated Livelihood Program (DILP) for the Livelihood Project for the Parent of Child Laborer in the Municipality of Bato, Leyte
Purchase of E-Loading Package for use in DOLE Integrated Livelihood Program (DILP) for the Livelihood Project for the Parent of Child Laborer in the Municipality of Bato, Leyte
Purchase of Office Supplies for use in the Municipal Budget Office, LGU, Bato, Leyte
Purchase of Office Supplies for use in the Bids and Awards Committee (BAC) Office, Bato, Leyte
Purchase of Various Materials for use in the Municipal Gymnasium, Bato, Leyte
Purchase of supplies for use during the 2023 Voluntary Blood Donation Activity on December 21, 2023 at the 3rd Floor, Municipal Hall Building, Bato, Leyte
Meal and Snacks for use during the 2023 Voluntary Blood Donation Activity on December 21, 2023 at the 3rd Floor , Municipal Hall Building, Bato, Leyte
| Sound System Services for use during the Socio-Cultural Activities in Connection with the LGU Christmas Party 2023, Bato, Leyte | [9 empty] | 2023-12-18 |  |  | 2023-12-22 | 2023-12-22 |  | 45000 |  |  | 40000
| Meal for use during the Christmas Party 2023 of LGU Officials and Employees on December 22, 2023, Bato, Leyte | [9 empty] | 2023-12-19 |  |  | 2023-12-22 | 2023-12-22 |  | 95400 |  |  | 95400
Kasalan ng Bayan
Purchase of various Agricultural Supplies for use in the Municipal Agriculture Office, LGU, Bato, Leyte
Purchase of various Materials for use in the Repair of Concrete Mini Canal along Port Road, Brgy. Iniguihan, Bato, Leyte
Purchase of Various Office Supplies for use in the Municipal Agriculture Office, LGU, Bato, Leyte
Purchase of Two (2) Units Jackhammer for use in the LGU, Bato, Leyte
Various Supplies DOLE
| Procurement of Various Equipment for Bato Fire Station (BFP). Bato, Leyte | Mayor's Office/ Hon. Nathaniel B. Gertos | Public Bidding |  | October 18- November 7, 2023 |  | November 7, 2023 | November 7, 2023 | November 8, 2023 | November 9-13, 2023 | November 15, 2023 | December 14, 2023 | November 21, 2023 |  |  | General Fund | 229409 |  | 229409 | 228559 |  | 228559 | Joselito T. Floren (BAMOTODA), Nathaniel B. Gertos (Mun. Mayor)End- User, Paulina J. Ruiz (SNARFA), ROLANDO BAGAY (BASAWCA), Marley M. Almosa (State Auditor II), Mrs. Hidelesa S. Tabale (Holy Child - MPC), |  | November 7, 2023 | November 7, 2023 | November 8, 2023 | November 9-13, 2023
sound
Completed
Total Alloted Budget of Procurement Activities | [16 empty] | 69544864.82
Total Contract Price of Procurement Actitvites Conducted | [16 empty] | 68984871.57
Total Savings (Total Alloted Budget - Total Contract Price) | [16 empty] | 559993.25
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
|  | Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | RUBY DE LOS SANTOS | [9 empty] | ATTY. LOUIE W. SUICO | [9 empty] | NATHANIEL B. GERTOS
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [9 empty] | Municipal Mayor

## Sheet1
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | LOCAL GOVERNMENT UNIT- BATO, LEYTE Procurement Monitoring Report as of July- December 2019
Code (PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Delivery/ Accept
| Construction of Bato Wet Market Phase II, Brgy. Iniguihan, Bato, Leyte | [19 empty] | MO/ Bryan Nile A. Gertos | Public Bidding |  | June 3-24, 2019 | June 13,2019 | 2019-06-24 | June 24,2019 | June 25,2019 | June 26,2019 | June 28,2019 | 2019-07-09 | 2019-07-03 | 2019-07-17 |  | Continuing-20% Dev't Fund |  |  | 1227660 |  |  | 1226801 | Wemia Seno (State Auditor IV), Hidelesa S. Tabale(HCMPC),Gilbert Rola (BAMOTODA), Paulina Ruiz(SNARFA), Marcelino Pagaduan(BASAWCA),Bryan Nile Gertos(Municipal Mayor) |  | 2019-06-13 |  | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-28 | 2019-07-09 | 2019-07-17 | Completed
| Purchase of printer for use in the BASCA office, LGU, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 5, 8, 2019 | [8 empty] | July 12, 2019 |  |  |  |  | 15000 | [13 empty] | Completed
| Purchase of construction materials for use in the Concrete Paving of Sitio Pathway, Sitio Dapdap, Brgy. Anahawan, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 5, 8, 2019 | [8 empty] | July 15, 2019 |  |  |  |  | 3900 | [13 empty] | Completed
| Purchase of hardware materials for use in the repair of Cebuana Day Care Center, Brgy. Cebuana, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 5-8, 2019 | [8 empty] | July 12, 2019 |  |  |  |  | 5475 | [13 empty] | Completed
| Purchase of signage for use in the SB office and MDRRM office, LGU, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 5-8, 2019 | [8 empty] | July 15, 2019 |  |  |  |  | 22400 | [13 empty] | Completed
| Provide meal and snacks during the Consultative Meeting with the LCE and the Kagawad on Social Services, Women and Family on the preparation of GAD Plan, BADAC Plan, Elderly & PWD and Budget for C.Y.2020 | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 5-8, 2019 | [8 empty] | July 15, 2019 |  |  |  |  | 19600 | [13 empty] | Completed
| Purchase of Bio Solution for use in the Solid Waste Management, LGU, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 6-9, 2019 | [8 empty] | July 16, 2019 |  |  |  |  | 25000 | [13 empty] | Completed
| Provide meal and snacks during the socio-cultural activities held on July 17, 2019 at Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 99900 | [13 empty] | Completed
| Purchase of tarpaulin printing for use in the 2019 Voluntary Blood Donation Program at HCKGCC, Bagongbayan (July 21, 2019) & Brgy. Osmena (July 26, 2019), Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 2500 | [13 empty] | Completed
| Provide meal and snaks during the 2019 Voluntary Blood Donation Program at HCKGCC, Bagongbayan (July 21, 2019) & Brgy. Osmena (July 26, 2019), Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 24200 | [13 empty] | Completed
| Purchase of various supplies for use in the 2019 Voluntary Blood Donation Program at HCKGCC, Bagongbayan (July 21, 2019) & Brgy. Osmena (July 26, 2019), Bato,Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 19, 2019 |  |  |  |  | 15670 | [13 empty] | Completed
| Provide meal and snacks during the socio-cultural activities held on July 26, 2019 at Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 99000 | [13 empty] | Completed
| Purchase of Desktop Computer for use in the office of the Municipal Assessor, LGU, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 50000 | [13 empty] | Completed
| Purchase of toner for use in the office of the Municipal Assessor, LGU, Bato, Leyte | [19 empty] | MO/ Nathaniel Gertos | Small Value Procurement |  | July 9-12, 2019 | [8 empty] | July 18, 2019 |  |  |  |  | 13600 | [13 empty] | Completed
`
|  | DEFINITION | [17 empty] | Remarks
|  | 1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [17 empty] | Programs and projects should be alligned with budget documents, and especially those posted at the PhilGeps.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evalutaion; post qualification; award of contract; contract preparation), Delivery/Acceptance Process, Payment Process
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
|  | 7. ABC - Approved Budget for the Contract | [17 empty] | Breakdown into mooe and co for tracking purposes; alligned with budget documents
|  | 8. Remarks - brief description of program or project | [17 empty] | Any remark that will help GPPB track programs and projects